## Schedule
Overshade |  |  | if anyone wants to change colors, click on the C cell; then click the dropdown and click on conditional formatting. then you can change colors
Mannedian Studios
Build Info: For more info pass by our office
|  |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4 |  |  | Week 5 |  |  | Week 6 |  |  | Week 7 |  |  | Week 8 |  |  | Week 9 |  |  | Week 10 |  |  | Week 11 |  |  | Week 12 |  |  | Week 13 |  |  | Week 14 |  |  | Week 15
WBS Item # | Task Name | Resource | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T | T |  | T | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T | T | W | T
Prep | preparing the team for the project
0,1.0 | learn unity basics | team | 1 | 1 | 1
0,1.1 | test github with unity | team | 1 | 1 | 1
Build 1 | Controls and input, saving and loading,Player and Enemy Loading
1,1.0 | Controls and input | Lilly |  |  |  | 1 | 1
1,1.1 | Movements(walking,Jumping | Lorrick |  |  |  | 1 | 1
1,1.2 | Jumping movement | Mahfuz |  |  |  | 1 | 1
1,1.3 | Dashing movement | Tom |  |  |  | 1 | 1
1,1.4 | Crouching movement | Lilly |  |  |  | 1 | 1
1,1.5 | Running movement | Lorrick | [5 empty] | 1 | 1
1,2.0 | P&E loading | Daniel | [5 empty] | 1 | 1
1,2.1 | Health | Mahfuz | [5 empty] | 1 | 1
1,2.2 | collision(P&E) | Mahfuz | [5 empty] | 1 | 1
1,3.0 | Saving & Loading | Daniel | [5 empty] | 1 | 1
1,3.1 | Creating Checkpoints | Daniel | [5 empty] | 1 | 1
1,3.2 | Respawn(P) | Tom | [5 empty] | 1 | 1
1,5 | Concept Art | Lilly | [5 empty] | 1 | 1 | 1
1,4.0 | Testing and Reviews 1 | Everyone | [7 empty] | 1 | 1
MILESTONE 1 |  | Producer
Build 2 | Physics Working, full audio implimented, level art complete, level complete,Sound complete
2,1.0 | Level Art complete | Lilly
2,1.1 | Characters complete | Lilly | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2,1.2 | Animation Xters | Tom | [9 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
2,1.3 | Background complete | Lilly | [9 empty] | 1 | 1 | 1
2,2.0 | Physics Working | Tom | [12 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 | 1
2,2.1 | Create a collision detection for the player | Lorrick | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1
2,3.0 | Sound Library | Lorrick | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1
2,3.1 | sfx library | Lorrick | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1
2,4 | fighting | Daniel | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2,5 | Level Concept & Design | Olotomiwa | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2,4.0 | Testing and Reviews 2 | Everyone | [25 empty] | 1 | 1
MILESTONE 2 |  | Producer
Build 3 | level progression
3,1.0 | Art | Lilly | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3,2.0 | Sound Library complete | Lorrick | [21 empty] | 1 | 1 | 1
3,2.0 | Repeat Build2(2X) | ALL | [24 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3,3.0 | Testing and Reviews 3 | Everyone
MILESTONE 3 |  | Producer
Build 4 | Load screen, Main Menu, Menu system working, no final graphics
4,1.0 | game loads,Splash Screen | Mahfuzur | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4,2.0 | New GameButton | Mahfuzur | [35 empty] | 1 | 1 | 1 |  | 1 | 1 | 1
4,2.1 | Choose character | Daniel | [37 empty] | 1 | 1 | 1 | 1 | 1
4,2.2 | Cutscene for level 1(Discarded) | Lilly
4,3.0 | Continue GameButton | Mahfuzur | [37 empty] | 1 | 1 | 1 | 1 | 1
4,4.0 | OptionButton | Mahfuzur | [38 empty] | 1 | 1 | 1 | 1
4,4.1 | SoundsButton | Tom | [37 empty] | 1 | 1 | 1 | 1 | 1
4,4.2 | gameControls | Lorrick | [36 empty] | 1 | 1 | 1 | 1 | 1 | 1
4,4.3 | PlayerJournal(Discarded) | Daniel
4,5.0 | Testing and Reviews 4 | Everyone | [42 empty] | 1 | 1 | 1
MILESTONE 4 |  | Producer
Build 5 | Alpha
Build 6 | Beta
Build 7 | RC 1

## Iterations
Iterations | Builds | Brief Explanation
1 | 1,1.0 | Controls and input
| 1,1.1 | Walking movement
| 1,1.2 | Jumping movement
| 1,1.3 | Dashing movement
| 1,1.4 | Crouching movement
| 1,1.5 | Running movement
| 1,2.0 | P&E loading
| 1,2.1 | Health
| 1,2.2 | collision(P&E)
| 1,3.0 | Saving & Loading
| 1,3.1 | Creating Checkpoints
| 1,3.2 | Respawn(P)
| 1,4.0 | Testing and Reviews 1
2 | 2,1.0 | Level Art complete
| 2,1.1 | Characters complete
| 2,1.2 | Animation Xters
| 2,1.3 | Background complete
| 2,2.0 | Physics Working
| 2,2.1 | Create a collision detection for the player
| 2,2.2 | Create boundaries for objects
| 2,2.3 | Create tags to identify objects
| 2,3.0 | Sound
| 2,3.1 | Background soundcomplete
| 2,3.2 | sfx library
| 2,4.2 | Testing and Reviews 2
3 | 3,1.0 | Background & GUI elmts Complete
| 3,2.0 | Sound Library complete
| 3,2.0 | Repeat Build2(9X)
| 3,3.0 | Testing and Reviews 3
| 4,1.0 | game loads,Splash Screen
| 4,2.0 | New GameButton
| 4,2.1 | Choose character
| 4,2.2 | level 1
| 4,3.0 | Continue GameButton
| 4,4.0 | OptionButton
| 4,4.1 | SoundsButton
| 4,4.2 | gameControls
| 4,4.3 | PlayerJournal
| 4,5.0 | Testing and Reviews 4

## Build List-History
Prep | Preparing the team for the project
0,1.0 | learn unity basics
0,1.1 | practice/test github with unity
Build 1 | Controls and input, saving and loading,Player and Enemy Loading
1.1 | Controls and input
1,1.1 | Walking movement
1,1.2 | Jumping movement
1,1.3 | Dashing movement
1,1.4 | Crouching movement
1,1.5 | Running movement
1.2 | P&E loading
1,2.1 | Health
1,2.2 | collision(P&E)
1.3 | Saving & Loading
1,3.1 | Creating Checkpoints
1,3.2 | Respawn(P)
Build 2 | Physics Working, full audio implimented, level art complete, level complete,Sound complete
2.1 | Level Art complete
2,1.1 | Characters complete
2,1.2 | Animation Xters
2,1.3 | Background complete
2.2 | Physics Working
2,2.1 | Create a collision detection for the player
2,2.2 | Create boundaries for objects
2,2.3 | Create tags to identify objects
2.3 | Sound
2,3.1 | Background soundcomplete
2,3.2 | sfx library
Build 3 | level progression
3.1 | Background & GUI elmts Complete
3.2 | Sound Library complete
3.2 | Repeat Build2(9X)
Build 4 | Load screen, Main Menu, Menu system working, no final graphics
4.1 | game loads,Splash Screen
4.2 | New GameButton
4,2.1 | Choose character
4,2.2 | level 1
4.3 | Continue GameButton
4.4 | OptionButton
4,4.1 | SoundsButton
4,4.2 | gameControls
4,4.3 | PlayerJournal
Build 5 | Alpha
Build 6 | Beta
Build 7 | RC 1

## Built List Dictionary
ID | Task | Dictionary | Dependencies | WBS ID
Prep | Preparing the team for the project |  | None | None
0,1.0 | learn unity basics |  | None | None
0,1.1 | practice/test github with unity |  | None | None
Build 1 | Controls and input, saving and loading,Player and Enemy Loading
1,1.0 | Controls and input | Setting up a basic Unity project, with everyone having access to it and making some research on version controls. A template could be used to create a player and adding in some movemnt scripts | prep | None
1,1.1 | Walking movement | A script for the basic movements | 1,1.0 | 2,0
1,1.2 | Jumping movement | A script for the basic movements | 1,1.0 | 2,0
1,1.3 | Dashing movement | A script for the basic movements | 1,1.0 | 2,0
1,1.4 | Crouching movement | A script for the basic movements | 1,1.0 | 2,0
1,1.5 | Running movement | A script for the basic movements | 1,1.0 | 2,0
1,2.00 | P&E loading | Creation of entity class which would allow the creation of players and enemies | None | 2.1,2
1,2.1 | Health | Each enemy should have properties like health | 1,2.0 | 2.1.2
1,2.2 | Collision(P&E) | Creating a script for the basic collision between player and enemy entity | 1,2.0 | 2,1.1
1,3.0 | Saving & Loading | Ability to save the current with player state and later loading it | 1,2.0 | 2,1.2
1,3.1 | Creating Checkpoints | Collision with a particular object or position to promp player to save | 1,3.0 | 2,1.1
1,3.2 | Respawn(P) | Incase player is killed, the ability to respawn from last save state | 1,3.1 | 2,1.2
1,4.0 | Testing and Reviews 1 | Testing the Build | Build 1 | None
Build 2 | Physics Working, full audio implimented, level art complete, level complete,Sound complete
2,1 | Level Art complete | Creating artwork for the environment of levels | None | 3.1.2
2,1.1 | Characters complete | Creating artwork of the players and entities | None | 3,0
2,1.2 | Animation Xters | Animating the various arts | 2,1 | 3,1,4
2,1.3 | Background complete | Creating artwork of the backgrounds of levels | None | 3,1.2
2,2.0 | Physics Working | Setup the physics in unity and implementing it | None | 2,1
2,2.1 | Create a collision detection for the player | Collision with any other object in the game | 2,2.3 | 2,1.1
2,2.2 | Create boundaries for objects | That is setting up objects in the world as shapes whether rectangles etc | None | 2,1.1
2,2.3 | Create tags to identify objects | Script | None | 2,1.1
2,3.0 | Sound | sound creation | None | 1,0
2,3.1 | Background sound complete | background sound created alongside the code to implement i to the game | None | 1.1
2,3.2 | SFX library | Creation of a library of sounds with all the different sound effects which would take place in the game | 2,3.0 | 1,1,1
2,4.0 | Testing and Reviews 2 | Testing the Build | Build 2 | None
Build 3 | level progression
3,1 | Background & GUI elements complete | Ensure that graphical elements are complete | 2,1.3 | all the 3's
3,2 | Sound Library complete | Sound Libraries for the game is complete | 2,3.0 | 1,1.1
3,2 | Repeat Build2(9X) | Repeat Build 2 for each level | Build 2 | 2,1.3
3,3.0 | Testing and Reviews 3 | Testing the Build | Build 3 | None
Build 4 | Load screen, Main Menu, Menu system working, no final graphics | At this level we would be putting all the different elements of our game together | Build 3
4,1.0 | Game loads & Splash Screen | Menu Interface created plus loading screen | 3,1 | 2,1.3
4,2.0 | New GameButton | Button is created and its functionalities are implemented | None | 2,1.3
4,2.1 | Choose character | Character selection and character switching functionality | None | 2,1.3
4,2.2 | Cutscene | A little animation for the 1st level | Build 3 | 2,1.3
4,3.0 | Continue GameButton | Button is created and its functionalities are implemented | None | 2,1.3
4,4.0 | OptionButton | Button is created and its functionalities are implemented | None | 2,1.3
4,4.1 | SoundsButton | button is created and its functionalities are implemented which basically a guide on how to play the game | None | 2,1.3
4,4.2 | GameControls | Button is created and its functionalities are implemented, which needs to be updated as the player plays | None | 2,1.3
4,4.3 | PlayerJournal | An interface with the credits and the version of the game | None | 2,1.3
4,4.4 | Credits | An interface containing information on our group | None | 2,1.3
4,5.0 | Testing and Reviews 4 | Testing the Build | Build 4 | None
Build 5 | Alpha
Build 6 | Beta
Build 7 | RC 1

## Milestone Plan
MileStone | Risks | Builds | Brief Explanation
1 | Lack of Knowledge in Unity | 1,1.0 | Controls and input
| Lack of knowlegde in version control systems | 1,1.1 | Walking movement
|  | 1,1.2 | Jumping movement
|  | 1,1.3 | Dashing movement
|  | 1,1.4 | Crouching movement
|  | 1,1.5 | Running movement
|  | 1,2.0 | P&E loading
|  | 1,2.1 | Health
|  | 1,2.2 | collision(P&E)
|  | 1,3.0 | Saving & Loading
|  | 1,3.1 | Creating Checkpoints
|  | 1,3.2 | Respawn(P)
|  | 1,4.0 | Testing and Reviews 1
2 | Too much workload on the artist in build 2.,1.0 | 2,1.0 | Level Art complete
| Not enough time to build 2,2.0 | 2,1.1 | Characters complete
|  | 2,1.2 | Animation Xters
|  | 2,1.3 | Background complete
|  | 2,2.0 | Physics Working
|  | 2,2.1 | Create a collision detection for the player
|  | 2,2.2 | Create boundaries for objects
|  | 2,2.3 | Create tags to identify objects
|  | 2,3.0 | Sound
|  | 2,3.1 | Background soundcomplete
|  | 2,3.2 | sfx library
|  | 2,4.2 | Testing and Reviews 2
3 | not enough time to nuild 10 levels. (Build 3,2.0) | 3,1.0 | Background & GUI elmts Complete
|  | 3,2.0 | Sound Library complete
|  | 3,2.0 | Repeat Build2(9X)
|  | 3,3.0 | Testing and Reviews 3
4 | confusing UI flow for users | 4,1.0 | game loads,Splash Screen
| bad game controls for users | 4,2.0 | New GameButton
|  | 4,2.1 | Choose character
|  | 4,2.2 | level 1
|  | 4,3.0 | Continue GameButton
|  | 4,4.0 | OptionButton
|  | 4,4.1 | SoundsButton
|  | 4,4.2 | gameControls
|  | 4,4.3 | PlayerJournal
|  | 4,5.0 | Testing and Reviews 4